DEPARTMENT OF INFORMATION TECHNOLOGY
THE UNIVERSITY OF HARIPUR

FINAL YEAR PROJECT (BS IT) — 30-DAY WORKLOAD EXECUTION PLAN
ECOSYN: A Carbon-Aware Smart Routing Framework for Serverless Cloud Computing

Project Team: Riffatullah & Muhammad Saad | Duration: 30 Days (4 Weeks) | Status: Approved (Form-2)

1. Executive Project Overview & Scope

EcoSyn is an intelligent request-routing framework designed to direct serverless function invocations to cloud data center regions characterized by lower carbon intensity (gCO2eq/kWh). This document presents a rigorous, 30-day daily workload plan designed to ensure total completion of the project, including software engineering, algorithmic modeling, comparative benchmark experiments, an interactive Streamlit web dashboard, and the full 5-chapter FYP thesis report for the University of Haripur IT Department examination panel.

2. High-Level 30-Day Milestone Phases

| Phase | Days | Core Focus & Primary Milestone | Lead Responsibilities |
| --- | --- | --- | --- |
| Phase 1: Foundations & Baselines | Days 1–7 | Config setup, cloud region profiles, carbon trace ingestion, Round-Robin and Latency-First baselines. | Saad (Architecture & Config) Riffatullah (Data & DB) |
| Phase 2: EcoSyn Core & Simulation | Days 8–14 | EcoSyn multi-objective algorithm, SLA guardrails, multi-region serverless cloud simulator. | Saad (Optimization Router) Riffatullah (Cloud Simulator) |
| Phase 3: Benchmarks & Dashboard | Days 15–21 | Head-to-head benchmark runs (1,000+ requests), thesis chart generation, interactive Streamlit UI. | Saad (Streamlit Dashboard) Riffatullah (Benchmark Runner) |
| Phase 4: Thesis Writing & Defense | Days 22–30 | Chapters 1–5 documentation, thesis formatting, PPT presentation design, viva demo rehearsals. | Joint (Chapters 1–5) Joint (Mock Defense & Slides) |

3. Complete 30-Day Daily Workload Schedule

| Day | Phase | Daily Workload & Specific Tasks | Team Roles | Expected Deliverables |
| --- | --- | --- | --- | --- |
| Day 1 | Foundations | Setup development environment (Python 3.10+, venv, Git). Finalize requirements.txt and verify IDE configs. | Saad: Git & venv setup Riffatullah: Tooling & dependencies | Clean Git repo, requirements.txt, venv active |
| Day 2 | Configuration | Build global config system (config/config.yaml). Define 4 cloud regions (eu-north-1, us-east-1, ap-south-1, sa-east-1) with PUE, coords, and prices. | Saad: Config schema design Riffatullah: Regional pricing & PUE research | config/config.yaml created and loaded via PyYAML |
| Day 3 | Data Ingestion | Build Carbon Tracker base class (BaseCarbonTracker) and offline trace loader (TraceCarbonTracker) to parse 24-hr regional grid data. | Saad: Base class architecture Riffatullah: CSV dataset curation & parsing | src/carbon_tracker/trace_tracker.py working |
| Day 4 | Live Carbon API | Integrate Electricity Maps / WattTime API connector with 5-minute in-memory caching to avoid rate limit locks. | Saad: REST API connector Riffatullah: Fallback logic & error handling | src/carbon_tracker/api_tracker.py functional |
| Day 5 | Baseline Routers | Implement Round-Robin Router (Baseline 1) and Greedy Latency-First Router (Baseline 2). | Saad: Latency-First router Riffatullah: Round-Robin router | src/router/round_robin.py and latency_first.py |
| Day 6 | Persistence Layer | Design SQLite / MySQL database schema using SQLAlchemy. Create models for invocation_logs and regional_stats. | Saad: Database manager class Riffatullah: ORM tables & migrations | src/storage/db_manager.py & models.py tested |
| Day 7 | Review & Sync | Write unit tests for carbon fetching and baseline routers. Conduct Week 1 supervisor check-in with demo. | Joint: Testing & weekly progress log | All Week 1 tests passing (pytest tests/) |
| Day 8 | Algorithm Design | Formulate EcoSyn mathematical multi-objective scoring function: Score(r) = w_c*C_r + w_l*L_r + w_p*P_r. | Saad: Normalization equations Riffatullah: Weight parameter validation | Mathematical specification documented in docs/ |
| Day 9 | SLA Guardrails | Implement Stage 1 SLA filtering logic in EcoSynRouter. Disqualify regions where latency > SLA_max. Fallback safety handler. | Saad: Core SLA filter logic Riffatullah: Edge-case tests (heavy loads) | EcoSyn SLA constraint filtering fully working |
| Day 10 | EcoSyn Router | Implement full EcoSynRouter class combining SLA filtering and Pareto multi-objective scoring. | Saad: Core router implementation Riffatullah: Dynamic weighting profiles | src/router/ecosyn_router.py completed |
| Day 11 | Cloud Simulation | Build Serverless Cloud Simulator: model function instances, cold starts (100-300ms), warm executions, and concurrency limits. | Saad: Multi-region simulator Riffatullah: Function execution lifecycle | src/simulator/cloud_environment.py operational |
| Day 12 | Energy & Emissions | Implement energy consumption model (PUE, active wattage, runtime) and carbon emission calculator (gCO2eq). | Saad: Carbon calculator formulas Riffatullah: Energy estimation verification | src/metrics/carbon_calculator.py functional |
| Day 13 | Workload Generator | Build synthetic workload trace generator modeling Poisson arrival patterns and bursty traffic spikes. | Saad: Arrival distribution engine Riffatullah: Real-world Azure trace synthesis | data/workload_traces/sample_workload.csv generated |
| Day 14 | Integration Test | Run 500 simulated function invocations through all 3 routers. Verify zero crashes, DB logging, and metric accuracy. | Joint: End-to-end integration test | 500-request pipeline validated with telemetry |
| Day 15 | Benchmark Suite | Develop automated benchmark runner (benchmarks/run_comparison.py) executing identical workloads across all routers. | Saad: Multi-policy execution runner Riffatullah: CLI argument parser & timing | benchmarks/run_comparison.py operational |
| Day 16 | Evaluation Metrics | Implement automated summary metrics: Carbon Reduction %, Average Response Time, Cost ($), and SLA Breach Rate. | Saad: Aggregator statistics Riffatullah: Result export to CSV/JSON | src/metrics/metrics_aggregator.py completed |
| Day 17 | Thesis Plots | Write automated plotting script (benchmarks/generate_charts.py) using Matplotlib/Seaborn. Generate 4 publication figures. | Saad: CDF & Pareto scatter plots Riffatullah: Carbon & regional distribution bars | High-res figures saved in reports/figures/ |
| Day 18 | Streamlit UI Setup | Initialize Streamlit web dashboard. Build sidebar controls (weights, SLA sliders, traffic size, region toggles). | Saad: Dashboard layout & controls Riffatullah: State management & config binding | src/dashboard/app.py skeleton running |
| Day 19 | World Map & Heatmap | Embed interactive world map and regional carbon intensity color heatmaps (Plotly geo scatter/choropleth). | Saad: Interactive map rendering Riffatullah: Live carbon status cards | Real-time global carbon visualizer completed |
| Day 20 | Live Dispatch Demo | Implement real-time request dispatch animation showing invocations being routed to green regions live. | Saad: Dynamic traffic dispatch visualizer Riffatullah: Telemetry feed & meter widgets | Interactive live routing demonstration completed |
| Day 21 | Stress Testing | Run 5,000+ request load test. Optimize DB batch insertion and freeze core codebase for defense. | Joint: Stress testing & code refactoring | Rock-solid software release; code frozen |
| Day 22 | Report Chapter 1 | Draft Chapter 1: Introduction (Background, Problem Statement, Aims & Objectives, Project Scope, Organization). | Saad: Problem statement & background Riffatullah: Aims, objectives & scope | Chapter 1 completed (approx. 8–10 pages) |
| Day 23 | Report Chapter 2 | Draft Chapter 2: Literature Review (Serverless cloud, green computing, existing routing heuristics, research gap). | Saad: Serverless & routing analysis Riffatullah: Green cloud & carbon tools survey | Chapter 2 completed with 20+ IEEE citations |
| Day 24 | Report Chapter 3 | Draft Chapter 3: System Design & Methodology (Architecture diagrams, sequence diagrams, algorithm pseudocode, math models). | Saad: Algorithm pseudocode & math Riffatullah: Flowcharts & DB ER diagrams | Chapter 3 completed with high-res diagrams |
| Day 25 | Report Chapter 4 | Draft Chapter 4: Implementation & Experimental Results (Setup, benchmarking analysis, graphs, discussion of findings). | Saad: Performance graphs & Pareto analysis Riffatullah: Experimental setup & parameters | Chapter 4 completed with benchmark charts |
| Day 26 | Report Chapter 5 | Draft Chapter 5: Conclusion & Future Work. Compile References in IEEE format and Appendices. | Saad: Conclusion & future directions Riffatullah: Reference compilation & formatting | Complete first draft of FYP Thesis Report |
| Day 27 | Thesis Review | Comprehensive proofreading, plagiarism check, formatting check per University of Haripur guidelines, supervisor review. | Joint: Revision & supervisor feedback | Final thesis report PDF compiled |
| Day 28 | Presentation Slides | Design 18–20 slide PowerPoint presentation for FYP defense (Problem, Architecture, Results, Live Demo preview). | Saad: System & results slides Riffatullah: Introduction & literature slides | defense_presentation.pptx finalized |
| Day 29 | Mock Defense Demo | Conduct dry-run presentation and live software demonstration. Practice answering examiner questions. | Joint: Rehearsal and Q&A drill | Smooth 15-minute presentation & 5-minute demo |
| Day 30 | Final FYP Submission | Submit bound thesis reports to Department of IT, commit final code to GitHub, archive project. | Joint: Final submission & department clearance | Official FYP Completion & Ready for External Viva |

4. Risk Assessment & Contingency Management

| Identified Risk | Impact | Likelihood | Mitigation Strategy |
| --- | --- | --- | --- |
| Carbon API Rate Limits or Downtime | High | Medium | EcoSyn implements local fallback caching and pre-packaged 24-hr historical grid traces so experiments never fail without internet. |
| Latency SLA Violations under High Carbon Drift | High | Low | Built-in Stage 1 SLA Guardrail automatically prunes regions exceeding SLA_max and falls back to lowest-latency region. |
| Delays in Report Writing & Defense Preparation | Medium | Medium | Report writing starts on Day 22 using modular chapter templates already aligned with Haripur IT department rubrics. |

5. Project Sign-off & Supervision Approvals

Student 1: __________________________ (Muhammad Saad)      Date: ______________

Student 2: __________________________ (Riffatullah)         Date: ______________

Supervisor: __________________________ (Faculty Member)     Date: ______________

FYP Coordinator / Head of Department: ___________________  Date: ______________